## Project Overview
PROJECT NAME
PURPOSE:
SCOPE:
FAILURE:

## Stakeholder Analysis
Stakeholder | Function | Interest | Contributions | Expectations | Level of interest | Power | Stratgic Importance | Strategy 30.09.05 | Responsible
Name | Stock-holder | Internal | Funding | EBIT Patent | 1 | 6 | 6 | Minimal effort | name
Name | Steering Committee | Internal | Reports Being helicopter | Prioritations Decisions Funding | 10 | 10 | 100 | Key Player | name
Name | Steering Committee | Internal | Prioritation Funding Decisions Being helicopter | EBIT Project to deliver | 9 | 10 | 90 | Key Player | name
Name | Steering Committee | Internal | Prioritation Funding Decisions Being helicopter | EBIT Project to deliver Patent | 7 | 10 | 70 | Key Player | name
Name | Steering Committee | Internal | Prioritation Funding Decisions Being helicopter | EBIT Project to deliver Patent | 7 | 10 | 70 | Key Player | name
Name | Project Manager | Internal | Driving force Reports Patent strategy | Interesting challenges Funding Decisions Market knowledge Competence | 10 | 10 | 100 | Key Player | name
Name | Project Member | Internal | Technical knowledge Market knowledge Interest Direct project work | Interesting challenges Competence | 10 | 10 | 100 | Key Player | name
Name | Patenting | Internal | Help with patent searches, competitor overview | Technology info help with patenting if applicable | 4 | 1 | 4 | Minimal effort | name
Name | Market | Internal | Market Information Brand name Market plan Price setting | Product & sales arguments | 10 | 10 | 100 | Key Player | name
Name | Market | Internal | Market Information Brand name Market plan Price setting | Product & sales arguments | 10 | 10 | 100 | Key Player | name
Name | Market | Internal | Market Information Brand name Market plan Price setting | Product & sales arguments | 10 | 10 | 100 | Key Player | name
Name | Customer | External | Definitions Test methods Application know how | Performance competitive price Application know how Additive know how | 1 | 6 | 6 | Minimal effort | name
Name | Distributor | External | Market Information Customer contact Market plan Sales plans Competitor pricing Training | Product & sales arguments EBIT Attractive products | 6 | 10 | 60 | Key Player | name
Name | Distributor | External | Market Information Customer contact Market plan Sales plans Competitor pricing Training | Product & sales arguments EBIT Attractive products | 6 | 10 | 60 | Key Player | name
Name | Distributor | External | Market Information Customer contact Market plan Sales plans Competitor pricing Training | Product & sales arguments EBIT Attractive products | 6 | 10 | 60 | Key Player | name
Name | Distributor | External | Market Information Customer contact Market plan Sales plans Competitor pricing Training | Product & sales arguments EBIT Attractive products | 6 | 10 | 60 | Key Player | name
Name | Distributor | External | Market Information Customer contact Market plan Sales plans Competitor pricing Training | Product & sales arguments EBIT Attractive products | 4 | 5 | 20 | Keep satisfied | name
Name | Distributor | External | Market Information Customer contact Market plan Sales plans Competitor pricing Training | Product & sales arguments EBIT Attractive products | 4 | 5 | 20 | Keep satisfied | name
Name | Suppliers | External | Equipment | Payment | 3 | 1 | 3 | Minimal effort | name
Name | Purchasing | Internal | Prices | Raw Material Information | 4 | 3 | 12 | Minimal effort | name
Name | Analytical lab | Internal | Analysis, method development | Specified tasks | 6 | 1 | 6 | Minimal effort | name
Name | Pilot Plant Manager | Internal | Capasity Cleaned functional kettle | Capacity Cleaned functional kettle | 1 | 1 | 1 | Minimal effort | name
Name | Plant Manager | Internal | Equipment Investments |  | 3 | 4 | 12 | Minimal effort | name
Name | Production Manager | Internal | Operators Equipment | Updated Movex Early information | 5 | 5 | 25 | Keep satisfied | name
Name | Logistics | Internal | Logistics |  | 3 | 1 | 3 | Minimal effort | name
Name | Regulatory | Internal | Regulatory Requirements | Information | 1 | 10 | 10 | Keep satisfied | name
Name | HSE | Internal | HSE requirements | Early information | 6 | 10 | 60 | Key Player | name
Name | Operators | Internal | Production | Simple production HSE "qualified" chemicals | 3 | 3 | 9 | Minimal effort | name
Name | Competitors | External | Nothing (indirectly information on products in market) | Nothing | 3 | 1 | 3 | Minimal effort | name
Note on F1: Ann Magrit Sommervold: Scale: 1-10 1: Not interested 4: Want to know result of project 7: Eager to know about progress 10: Will seek to activly participate
Note on G1: Ann Magrit Sommervold: Scale: 1-10 1: Will not influence decisions 4: May contribute to changes 7: May demand large changes 10: May stop the project
Note on H1: Ann Magrit Sommervold: Strategic importance = Level of interest * Power RED = Key Player Yellow = Keep informed/satisfied GREEN = Minimal effort
Note on I1: Ann Magrit Sommervold: RED (>40) Yellow (<18,40>) Green (<18)

## RISK Analysis
FAILURE:
F1
F2
RISK = consequence * probability (1=low, 10=highest)
|  | RISK < 18 | P < 3.5 | C < 3.5 |  |  | P < 3.5 | C < 3.5
|  | RISK < 18,39> | 3.5 < P < 6.5 | 3.5 < C < 6.5 |  |  | 3.5 < P < 6.5 | 3.5 < C < 6.5
|  | RISK > 40 | 6.5 < P | 6.5 < C |  |  | 6.5 < P | 6.5 < C
[5 empty] | 2005-09-30 |  |  |  | 2005-10-30 |  |  |  | 2005-11-30
| ID | RISK FACTORS | Probability | Concequence | RISK | ACTION | Probability | Concequence | RISK | ACTION | Probability | Concequence | RISK
F1 | R1 | Fail to identify competitors best products | 6 | 3 | 18 | Initiate distributors to look for what is commonly used in the market | 6 | 3 | 18 |  | 6 | 3 | 18
F1 | R2 | Fail to identify products with performance equal or better than competitors products | 5 | 7 | 35 |  | 5 | 7 | 35 |  | 5 | 7 | 35
F1 | R3 | Fail to document findings properly, in order for receiver to understand purpose of | 5 | 7 | 35 |  | 5 | 7 | 35 |  | 5 | 7 | 35
F2 | R4 | Fail to distribute products effectively into the market | 7 | 8 | 56 | Ask distributors on input to how it should be done prior to launch Use Live Meeting as tool to launch new additives Introduce e-marketing ? | 7 | 8 | 56 |  | 7 | 8 | 56
F2 | R5 | Fail to be acknoledged as a serious supplier | 4 | 8 | 32 |  | 4 | 8 | 32 |  | 4 | 8 | 32
M1 | R6 | Fail to start up lab equipment | 5 | 2 | 10 |  | 5 | 2 | 10 |  | 5 | 2 | 10
M2 | R7 | Fail to include all in training | 1 | 4 | 4 |  | 1 | 4 | 4 |  | 1 | 4 | 4
M2 | R8 | Poor teacher for specific theory day | 5 | 6 | 30 | Use different training materials | 3 | 6 | 18 |  | 3 | 6 | 18
M2 | R9 | Illness | 3 | 6 | 18 |  | 3 | 6 | 18 |  | 3 | 6 | 18
M2 | R10 | Someone in project quits | 2 | 10 | 20 |  | 2 | 10 | 20 |  | 2 | 10 | 20
M3 | R11 | Not able to identify market price | 8 | 3 | 24 |  | 8 | 3 | 24 |  | 8 | 3 | 24
M3 | R12 | Fail to identify target customers | 2 | 9 | 18 | Initiate distributors to identify potential customers | 2 | 9 | 18 |  | 2 | 9 | 18
M3 | R13 | Change distributor | 3 | 9 | 27 |  | 3 | 9 | 27 |  | 3 | 9 | 27
M3 | R14 | Failure to inspire distributor to contribute | 7 | 9 | 63 | Include distributors early in project and inspire to contribution | 6 | 9 | 54 |  | 6 | 9 | 54
M4 | R15 | Misunderstand customers challenge and needs | 5 | 9 | 45 | Initiate dialog with direct customers like …. | 4 | 9 | 36 |  | 4 | 9 | 36
M5 | R16 | Not able to locate adequate equipment | 4 | 8 | 32 |  | 4 | 8 | 32 |  | 4 | 8 | 32
M5 | R17 | Test-equipment too expensive for steering committee | 4 | 9 | 36 |  | 4 | 9 | 36 |  | 4 | 9 | 36
M5 | R18 | Delays due to late arrival of test equipment | 8 | 6 | 48 | Find and contact potential customer early to decide on equipment | 8 | 6 | 48 |  | 8 | 6 | 48
M5 | R19 | Serious difficulty with equipment | 6 | 5 | 30 |  | 6 | 5 | 30 |  | 6 | 5 | 30
M6 | R20 | None of existing products suitable as additive | 1 | 8 | 8 |  | 1 | 8 | 8 |  | 1 | 8 | 8
M7 | R22 | Not able to develop IP strategy | 2 | 5 | 10 |  | 2 | 5 | 10 |  | 2 | 5 | 10
M7 | R23 | Miss possibility to patent | 7 | 5 | 35 |  | 7 | 5 | 35 |  | 7 | 5 | 35
M7 | R24 | Dark space analyses hinders us from completing the project | 4 | 10 | 40 | Patent day once a month Active patent searches | 4 | 10 | 40 |  | 4 | 10 | 40
M8 | R25 | No new products identified | 4 | 6 | 24 |  | 4 | 6 | 24 |  | 4 | 6 | 24
M8 | R26 | Raw material cost for new products too high or chances for rapid price increases | 7 | 8 | 56 | Evaluate several raw material suppliers Use cost evaluation as critical performance criteria | 7 | 8 | 56 |  | 7 | 8 | 56
M12 | R27 | Inadequate process evaluation | 4 | 7 | 28 |  | 4 | 7 | 28 |  | 4 | 7 | 28
M13 | R28 | Production fails to produce product | 4 | 7 | 28 | Evaluate potential outsourcing | 4 | 7 | 28 |  | 4 | 7 | 28
| R29 | Change of strategic focus | 5 | 5 | 25 |  | 5 | 5 | 25 |  | 5 | 5 | 25
| R30 | Inadequate regulatory evaluation | 7 | 7 | 49 | Ask for regulatory information together with ordering of raw materials | 7 | 7 | 49 |  | 7 | 7 | 49
| R31 | Inadequate HSE evaluation | 5 | 7 | 35 |  | 5 | 7 | 35 |  | 5 | 7 | 35

## Milestone Planning
# | MILESTONES |  | Largely involved | Within/ date | Completed | Status 30.09.05 | Comment
M1 | Milestone 1
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M2 | Milestone 2
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M3 | Milestone 3
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M4 | Milestone 4
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M5 | Milestone 5
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M6 | Milestone 6
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M7 | Milestone 7
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M8 | Milestone 8
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M9 | Milestone 9
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M10 | Milestone 10
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M11 | Milestone 11
Sub-Milestone a
Sub-Milestone b
Sub-Milestone c
M12 | Milestone 12